| Item | Activity Detail | To Take Place By | Meeting Reported to | Completed |
| --- | --- | --- | --- | --- |
| Monitoring and oversight of Code of Ethics in Alliance | Briefings on the impact of the Code of Ethics in the Alliance and the implementation of the cultural change programme. | - | 22 Sep 2014 | ( |
|  |  | - | 21 Nov 2014 | ( |
|  |  | - | 29 Oct 2015 |  |
| Complaint dip sampling | Two Independent Members to dip sample complaint cases from each Force monthly and report back to the Committee. | - | Standing Item | - |
|  | 11 complaints reviewed on 8 October 2014 | Oct 2014 | 21 Nov 2014 | ( |
|  | Complaints were reviewed on 5 November 2014 | Nov 2014 | 21 Nov 2014 | ( |
|  | Complaints were reviewed on 3 December 2014 | Dec 2014 | 11 Feb 2015 | ( |
|  | 7 complaints reviewed on 14 January 2015 | Jan 2015 | 11 Feb 2015 | ( |
|  | 5 complaints reviewed on 18 February 2015 | Feb 2015 | 30 Apr 2015 | ( |
|  | 9 complaints reviewed on 11 March 2015 | Mar 2015 | 30 Apr 2015 | ( |
|  | 2 complaints reviewed on 21 April 2015 | Apr 2015 | 23 Jul 2015 |  |
|  | 6 complaints reviewed on 13 May 2015 | May 2015 | 23 Jul 2015 |  |
|  | 4 complaints reviewed on 10 June 2015 | Jun 2015 | 23 Jul 2015 |  |
|  | 5 complaints reviewed on 8 July 2015 | Jul 2015 | 23 Jul 2015 |  |
| Public attendance at Committee meetings | Procedure for members of the public attending Committee meetings to be agreed. | - | 21 Nov 2014 | ( |
| HMIC Review of Professional Standards | Update the Committee on the review. | - | 21 Nov 2014 | ( |
|  | To be circulated to the Committee. | Dec 2014 | 11 Feb 2015 | ( |
| Use of covert powers | To circulate to Committee members the Surveillance Commissioner’s report in response to the use of covert powers and compliance with the Regulation of Investigatory Powers Act (RIPA). | Nov 2014 | - | ( |
|  | Presentation and briefing on the use of covert powers within the Alliance. | - | 11 Feb 2015 | ( |
| Complaint timescales and local resolution | Presentation to the Committee on compliance with complaint timescales in the Alliance and use of local resolution. | - | 21 Nov 2014 | ( |
|  | Performance data on complaints and conduct to be provided to the Committee. | - | Standing Item | - |
| HMIC Crime Data Integrity Review | Disseminate report to Committee. | - | 21 Nov 2014 | ( |
|  | Provide Force Action Plan. | - | 21 Nov 2014 | ( |
|  | Provide updated Force Action Plan. | Apr 2015 | - | ( |
|  | Independent Members to visit the Warwickshire or West Mercia Communications Centre to watch the call handling process and how incoming calls are assessed and prioritised. Then to meet with the Alliance Crime Bureau Manager and the Alliance Registrar. | Feb 2015 | 11 Feb 2015 | ( |
|  | Committee Members to participate in either a ride along, foot patrol or visit to the control room to listen in to calls. | Apr - Jul 2015 | 30 Apr 2015 | ( |
|  |  |  | 23 Jul 2015 |  |
|  | Committee Members to provide an update report on the crime recording process in the Alliance, following visits/briefings and consider the recommendations made in the HMIC review and action plan. | - | 11 Feb 2015 | ( |
|  |  | - | 30 Apr 2015 | ( |
|  |  | - | 23 Jul 2015 |  |
| Internal Professional Standards Department review | Update the Committee on the review. | - | 21 Nov 2014 | ( |
|  | Report to Committee on the outcomes of the review. | - | 11 Feb 2015 | ( |
|  | Update on review. | - | 23 Jul 2015 |  |
| Rape ‘no crimes’ | To agree Terms of Reference for a review of ‘no crimes’ in rape cases in the Alliance for 2012/13. | - | 21 Nov 2014 | ( |
|  |  |  | 11 Feb 2015 | ( |
|  | To review ‘no crimes’ in rape cases in the Alliance for 31 October 2013 – 31 October 2014. 9 cases reviewed on 7 April 2015, with three cases thought to be incorrectly no crimed. | Apr 2015 | 30 Apr 2015 | ( |
|  | To review the remaining 18 cases for the same period. | Oct 2015 | 29 Oct 2015 |  |
| HMIC Police Integrity and Corruption Inspection | Report to be circulated to the Committee | Feb 2015 | - | ( |
|  | Briefing from CC David Shaw and ACC Amanda Blakeman | Feb 2015 | 11 Feb 2015 | ( |
|  | Update on Alliance progress against action plan. | - | 23 Jul 2015 |  |
| Child Sexual Exploitation | Presentation on child sexual exploitation to be provided to the Committee. | - | 30 Apr 2015 | ( |
| PCC Overview | PCCs to provide an overview of their role, practical priorities and how the role has changed. | - | 30 Apr 2015 | Cancelled by Members |
| Service Delivery | Members to be provided with performance information for service delivery. | - | 30 Apr 2015 | ( |
| Interception of Communication Inspection | Report and Action Plan to be circulated to the Committee. | April 2015 | - | ( |
|  | CC David Shaw to brief the Committee on the Report and Action Plan. | - | 23 Jul 2015 |  |
| Out of Court Disposals Group | Invite a member of the West Mercia group to a Committee meeting. Invite a member of the Warwickshire group to a Committee meeting. | - | 23 Jul 2015 |  |
| Overall use of force CS/Pava Taser Firearms Dogs | IPCC Study into Police use of force due to be published autumn 2015. | - | 29 Oct 2015 |  |
|  | Independent review of use of force forms. | Dec 2015 | 28 Jan 2016 |  |
|  | Relevant documents to be circulated to the Committee at the appropriate time. | - | - |  |
| Stop and search | Presentation from a representative of the Alliance Stop and Search Board. | - | 29 Oct 2015 |  |
| Terrorism | Presentation on terrorism to be provided to the Committee. | - | 29 Oct 2015 |  |
| Media Training | Members to be provided with media training. | Dec 2015 | - |  |
| HMIC Police Integrity and Leadership Thematic Inspection | Terms of Reference being drafted. Inspection details and final report will come to Committee when available. | - | TBC |  |
| Independent Custody Visitors | Details of the independent custody visiting process to be provided to the Committee, following completion of the review of the Warwickshire and West Mercia schemes. | Jan 2016 | 28 Jan 2016 |  |